## Sheet1
Burndown chart
Time in days
Day | Planned | Actual
Monday- sprint planning | 28 | 28
Tuesday | 26 | 27
Wednesday | 24 | 27
Thursday | 22 | 27
Friday | 20 | 21
Monday | 18 | 21
Tuesday | 16 | 20
Wednesday | 14 | 13
Thursday | 12 | 10
Friday | 10 | 8
Monday | 8 | 6
Tuesday | 6 | 4
Wednesday | 4 | 3
Thursday | 2 | 0
Friday- sprint review | 0 | 0